## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2205-swen-261-01-d racecarBackwards
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | SW, GV 3/6 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | SW, SM 3/6 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | SW, VM, SM 3/6 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | SW, SM, GV 3/6 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | SW, SM 3/6 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | SW, AY 3/9 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | AY, VM 3/9 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | GV, SM, AY 3/7 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | GV, AY 3/7 | Pass | GV 3/30 WL 4/6 only had 8 pieces each, but is already fixed in new branch. | Pass | SM, GV 4/11
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | GV, SW, AY 3/7 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | GV, SM 3/7 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | VM, SW, 3/9 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | VM, SW, 3/9 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | VM, SW, 3/9 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | VM, SW, 3/9 | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
As a player, I want to sign out of the game so I can stop playing. | Given that I am signed in when I can see the nav bar then I will see a way to sign out. |  |  | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given that I want to sign out when I click the sign out link then I should be signed out of the application. |  |  | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
As a Game I want to end so that the players know the results of the game, as well as so I can be freed from memory. | Given I am an active game when I am ended then the reason can be stored. |  |  | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given I am a game when I am ended then the reason will be accessable. |  |  | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
| Given I have access to a game then when I look through that game then I can tell if it is still active. |  |  | Pass | GV 3/30 WL 4/6 | Pass | SM, GV 4/11
As a player, I want to be able to manually resign at any time so that I can end the game session. | Give that I have utterly lost this game when I click the Resign button then the current game should end. |  |  | Fail | GV 3/30 Ability to resign is not yet implemented. | Pass | SM, GV 4/11
As a piece, I want to make a legal move so I can traverse the board. | Given that there is a vacant black space diagonally adjacent from me when I attempt to place my piece there then my piece will be moved. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that an opponent's piece is diagonally adjacent and there is an empty space beyond that when I attempt to capture the piece then the opponent's piece will be removed and my position will be moved. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that a jump move is available when it is my turn then I should choose to jump over any other movement. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that several jump choices are available when I choose to make a jump move then I can freely choose between any available jumps. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that a jump move is possible after completing a jump move when I complete my jump move then I must make another jump move. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that I'm a single piece when I make it to the other side of the board then I should be promoted to a king piece. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that I'm a single piece when I choose to make a simple move or jump move then I can only move diagonally forward. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that I'm a king piece when I choose to make a simple move or jump move then I can move both diagonally forward and diagonally backwards. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
| Given that I have a valid move when I make a simple move then I can only move one diagonally vacant space away. |  |  | Fail | GV 3/30 Movement Logic implemented, but Ajax calls are not yet implemented to properly test. | Pass | SM, GV 4/11
As a player I want to move a piece so I can progress the game. | Given it is my turn when I make a legal move then the game board will update. |  |  | Fail | GV 3/30 Ajax calls are still being implemented. | Pass | SM, GV 4/11
| Given it is my turn when I attempt to make an illegal move then nothing will happen and I will be told it is an illegal move. |  |  | Fail | GV 3/30 Ajax calls are still being implemented. | Pass | SM, GV 4/11
| Give it is not my turn when I attempt to move a piece then nothing will happen. |  |  | Fail | GV 3/30 Ajax calls are still being implemented. | Pass | SM, GV 4/11
| Given I have no valid moves when it is my turn then I will automatically forfeit the match. |  |  | Fail | GV 3/30 Ajax calls are still being implemented. | Pass | SM, GV 4/11
Enhancement: As a user I want to spectate a game so that I can be entertained. | Given I have signed in when I view the Home page then I can spectate a player by selecting it on the Home page. |  |  |  |  | Pass | SW 4/14
| Given the player I selected is in a game when I select them then I will be shown the current game. |  |  |  |  | Pass | SW 4/14
| Given the player I selected is not in a game when I select them then I will be sent back to the home page with an error. |  |  |  |  | Pass | SW 4/14
| Given I am spectating a game when a turn is taken then the board will be updated. |  |  |  |  | Pass | SW 4/14
| Given I am spectating a game when the game ends then I will be shown the end state |  |  |  |  | Pass | SW 4/14
| Given I am spectating a game when I choose to stop spectating the game then I will be sent back to the Home page. |  |  |  |  | Pass | SW 4/14